## Slide 1
Agentic AI MVP Programme
A 9-month plan to build 4 AI agents for R&D IT platforms, starting with 3DP and BIKG
4
AI Agents
2-3
Primary Platforms
6
FTEs
9
Months
DURATION
March – November 2026
PRIMARY PLATFORMS
3DP, BIKG
AGENTS
Test Intelligence, Knowledge Library, Ingestion, Auto-Lineage
EXTENSIBILITY
Additional platforms tailored during discovery
1

## Slide 2
Team Structure
Core team of 6 FTEs with part-time platform SME support across the 9-month programme.
Role | Count | Name / Location
Tech Lead / Architect | 1 | Devesh
Senior AI/ML Engineer | 2 | Abdalla Abdakarim + 1 Offshore
Backend Engineer | 2 | Offshore
Frontend Engineer / Tester | 1 | Offshore
Part-time SMEs: 3DP (20%), BIKG (20%), AI Ops (10%), Data Foundation (10%) — additional platform SMEs engaged during discovery phase as needed.
Team Allocation by Phase
Role | Phase 1 (Mar-May) | Phase 2 (Jun-Aug) | Phase 3 (Sep-Nov)
Devesh | Architecture, AI Ops integration | RAG + Ingestion architecture | Graph DB, lineage design
Abdalla | LLM test generation, prompts | RAG pipeline, Q&A | Lineage extraction
ML Engineer | Synthetic data generation | Schema inference | Impact analysis
Backend Eng 1 | Test generation APIs | Knowledge search APIs | Lineage storage APIs
Backend Eng 2 | Test runner service | Ingestion mapping APIs | Lineage query APIs
Frontend / Tester | Test dashboard, QA | Chat UI, Mapping UI, QA | Lineage graph UI, QA
2

## Slide 3
4 Agents for R&D IT Platforms
A portfolio of Agentic AI opportunities selected for high impact on primary platforms (3DP, BIKG), with flexibility to extend to additional platforms during discovery.
Rank | Agent | Score | Primary Platforms | Process Bottleneck Addressed
#1 | Test Intelligence Agent | 4.30 | 3DP, BIKG | Slow Validation and Release Cycles
#5 | Knowledge Library Companion | 4.00 | 3DP, BIKG | Lack of Reusable & Standardised Pipeline Components
#6 | Ingestion Companion | 3.80 | 3DP, BIKG | Time-Consuming Data Ingestion and Preparation
#8 | Auto-Lineage Agent | 3.75 | 3DP, BIKG | Manual Data Management and Traceability
Platform Strategy
3DP (Primary)
BIKG (Primary)
Additional platforms identified during discovery
Extensibility: All agents are designed with a platform-agnostic architecture. During discovery workshops, we will identify 1-2 additional platforms where these agents can be tailored and deployed.
Target Outcomes
25%
Less Manual Testing
50%
Faster Answers
25-30%
Faster Ingestion
15-25%
Less Manual Traceability
3

## Slide 4
Agent Benefits: 3DP & BIKG
Detailed value proposition for the two primary pilot platforms.
Agent | 3DP Benefit | BIKG Benefit
Test Intelligence Agent | Generate regulatory validation test cases | Generate KG query test cases
 | Synthetic patient data for submission testing | Synthetic biological entity data
 | Find similar past submission test failures | Find similar failed BIKG queries
Knowledge Library Companion | "How do I prepare a Module 3 submission?" | "How do I query gene-disease relationships?"
 | Search regulatory guidelines, SOPs | Search biological ontologies, data dictionaries
 | Summarize 500-page FDA guidance docs | Summarize pathway documentation
Ingestion Companion | Auto-detect regulatory data schemas | Auto-detect biological data schemas
 | Map source data to submission format | Map source data to KG ontologies
 | Improve ingestion prep by 25-30% | Reduce manual data mapping
Auto-Lineage Agent | Regulatory audit trail (FDA/EMA requirement) | Gene → Protein → Drug lineage
 | FAIR compliance evidence | Data provenance tracking
4

## Slide 5
Main steps to mobilise and build Agentic AI
A structured plan to build 4 AI agents, co-design Human+AI workflows, and enable change across R&D IT.
March – May 2026
Phase 1: Test Intelligence Agent
OBJECTIVE
Build foundational testing automation for 3DP and BIKG, validating the agentic approach with high-impact MVP.
ACTIVITIES
• Conduct discovery workshops with 3DP, BIKG teams • Build LLM-powered test generation, synthetic data • Integrate with 3DP and BIKG platforms
OUTPUTS
1. Test Intelligence Agent deployed 2. 25% reduction in manual test effort 3. Reusable prompts & templates
June – August 2026
Phase 2: Knowledge Library + Ingestion
OBJECTIVE
Scale to knowledge management and data ingestion, enabling self-service docs and automated data onboarding.
ACTIVITIES
• Build RAG pipeline for document search and Q&A • Build schema inference and auto-mapping • Design human-in-the-loop review workflows
OUTPUTS
1. Knowledge Library with docs indexed 2. Ingestion Companion with auto-schema 3. 50% faster answers, 25-30% faster ingestion
September – November 2026
Phase 3: Auto-Lineage Agent
OBJECTIVE
Complete the data lifecycle with lineage tracking, enabling FAIR compliance and regulatory audit readiness.
ACTIVITIES
• Define lineage requirements for regulatory and biological data • Build graph-based lineage extraction • Implement FAIR evidence generation
OUTPUTS
1. Auto-Lineage Agent deployed 2. FAIR compliance evidence for 3DP 3. Training materials for scaling
5

## Slide 6
Proposed timelines for 9-month mobilisation
Workstream | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Opportunity Selection & Discovery | ■ | ■◆ |  |  |  |  |  |  | 
Phase 1: Test Intelligence Agent | ■ | ■ | ■◆ |  |  |  |  |  | 
Discovery & Architecture | ■ |  |  |  |  |  |  |  | 
LLM Test Gen & Synthetic Data |  | ■ |  |  |  |  |  |  | 
Platform Integration & Pilot |  |  | ■ |  |  |  |  |  | 
Phase 2: Knowledge Library |  |  |  | ■ | ■ | ■◆ |  |  | 
Phase 2: Ingestion Companion |  |  |  | ■ | ■ | ■◆ |  |  | 
Phase 3: Auto-Lineage Agent |  |  |  |  |  |  | ■ | ■ | ■◆
Graph DB & Lineage Design |  |  |  |  |  |  | ■ |  | 
Extraction & Visualization |  |  |  |  |  |  |  | ■ | 
FAIR Compliance & Deployment |  |  |  |  |  |  |  |  | ■
Training & Enablement |  |  |  |  |  |  |  | ■ | ■◆
◆ Milestone
■ Phase 1: Test Intelligence
■ Phase 2: Knowledge + Ingestion
■ Phase 3: Auto-Lineage
6

## Slide 7
Success Metrics
Key performance indicators for each agent MVP.
Phase | Agent | Metric | Target
Phase 1 | Test Intelligence Agent | Manual test effort reduction | 25%
 |  | Test coverage increase | 15%
 |  | Platforms integrated | 3DP, BIKG + discovery
Phase 2 | Knowledge Library Companion | Time-to-answer reduction | 50%
 |  | Documents indexed | 1000+
 |  | Query success rate | 80%
Phase 2 | Ingestion Companion | Ingestion prep time reduction | 25-30%
 |  | Schema inference accuracy | 85%
 |  | Platforms supported | 3DP, BIKG + discovery
Phase 3 | Auto-Lineage Agent | Manual traceability reduction | 15-25%
 |  | Lineage coverage | 3DP, BIKG + discovery
 |  | FAIR compliance | Audit-ready
7

## Slide 8
Key Milestones
9-month delivery roadmap with clear deliverables for each phase.
Month | Phase | Milestone | Key Deliverable
M1 (Mar) | Phase 1 | Discovery Complete | Requirements from 3DP, BIKG + additional platforms identified
M2 (Apr) | Phase 1 | Test Gen API Live | LLM test generation working with Claude
M3 (May) | Phase 1 | ◆ Agent 1 Pilot | 3DP + BIKG using Test Intelligence Agent
M4 (Jun) | Phase 2 | RAG + Schema Ready | Docs crawled, schema detection working
M5 (Jul) | Phase 2 | Q&A + Mapping Live | Knowledge search + ingestion mapping APIs
M6 (Aug) | Phase 2 | ◆ Agents 2 & 3 Pilot | Knowledge Library + Ingestion Companion live
M7 (Sep) | Phase 3 | Graph DB Ready | Lineage schema deployed to Neptune/Neo4j
M8 (Oct) | Phase 3 | Lineage Extraction | Metadata captured across platforms
M9 (Nov) | Phase 3 | ◆ All 4 Agents Live | FAIR compliance, full deployment, training complete
8